## Sheet1
Sprint 2 Backlog Items Hour Tracker | [6 empty] | Personal Hour Tracker
| Est. | 2016-09-29 | 2016-10-05 | 2016-10-07 | 2016-10-12 | 2016-10-17 |  | Expected | Worked | Performance
RPS Fix Choices | 2 |  |  |  | 2 | 2 | Christian | 8 | 9.5 | 118.8%
RPS Add extra animations | 4 |  |  |  |  | 1 | Katie | 10 | 10.5 | 105%
RPS Testing | 2 |  |  |  |  | 1 | Jacob | 12 | 9 | 75%
Code Repo Access | 0.5 |  |  | 9 |  |  | Colin | 12 | 9 | 75%
Sprint Demo | 2 |  |  |  | 2 | 2 | Adrian | 10 | 6.5 | 65%
Sprint Presentation | 2 |  |  |  |  | 3 | Casey | 12 | 7.5 | 62.5%
Sprint Admin | 3 | 6 | 2 |  |  |  | Team | 64 | 52 | 81.25%
High-Low Code Exploration | 10 |  |  |  | 2 | 2
Fix Star Wars Demo | 1 |  |  | 1
Explore Capabilities | 15 |  |  |  | 2 | 2
K-5 Emotions | 10
Animations | 10 |  | 4 | 1 | 4 | 4
Total Spent |  | 6 | 6 | 11 | 12 | 17
Total Remaining | 61.5 | 55.5 | 49.5 | 38.5 | 26.5 | 9.5
Burndown | Initial | 2016-09-29 | 2016-10-05 | 2016-10-07 | 2016-10-12 | 2016-10-17
RPS Fix Choices | 2 | 2 | 2 | 2 | 0 | 0
RPS Add extra animations | 4 | 4 | 4 | 4 | 4 | 3
RPS Testing | 2 | 2 | 2 | 2 | 2 | 1
Code Repo Access | 0.5 | 0.5 | 0.5 | 0 | 0 | 0
Sprint Demo | 2 | 2 | 2 | 2 | 0 | 0
Sprint Presentation | 2 | 2 | 2 | 2 | 2 | 0
Sprint Admin | 3 | 0 | 0 | 0 | 0 | 0
High-Low Code Exploration | 10 | 10 | 10 | 10 | 8 | 6
Fix Star Wars Demo | 1 | 1 | 1 | 0 | 0 | 0
Explore Capabilities | 15 | 15 | 15 | 15 | 13 | 11
K-5 Emotions | 10 | 10 | 10 | 10 | 10 | 10
Animations | 10 | 10 | 6 | 5 | 1 | 0
| 61.5 | 58.5 | 54.5 | 52 | 40 | 31